## in
Custom field (Product Portfolio) | Custom field (Product Team) | Custom field (Quarterly Roadmap) | Summary
Unified Management | Command | 21-Q2 | HyperV Infrastructure Data in Devices
Unified Management | Command | 21-Q2 | VMWare Infrastructure in Devices
Security Management | Security Management | 21-Q4 | Fortify Assessment Standard : Network Device Discovery
Security Management | Security Management | 21-Q4 | Fortify Assessment Standard : Web Content Filtering Assessment
Security Management | Security Management | 21-Q4 | Fortify Assessment Standard : Cloud Assessment
Security Management | Security Management | 21-Q4 | Fortify Assessment Standard : Endpoint Risk Categories (II)
Security Management | Security Management | 21-Q2 | Fortify for Risk Platform - MVP 1.0 - Vulnerability Scanning through Command Integration
Unified Management | Control | 21-Q2 | Integrate unattended access agents with Datto RMM
Unified Management | Control | 21-Q2 | Update Backstage by enhancing the existing feature set and making it easier to use
Unified Management | Control | 21-Q2 | Add ability for partners to save and install differently configured Control agent installers on endpoints
Unified Management | Command | 21-Q2 | Script Engine Improvements: addition of different automate style functions
Unified Management | Command | 21-Q1 | Implement Script Editor
Business Management | Business Management | 21-Q2 | Marketplace reconciliation with Manage agreements
Unified Management | Command | 21-Q3 | Work assignment to NOC from any service board
Unified Management | Command | 21-Q3 | Avoid device duplication in Manage
Unified Management | Command | 21-Q2 | Manage/Command Contact Sync
Unified Management | Command | 21-Q2 | Fusion Patching GA
Unified Management | Command | 21-Q2 | Partner Defined Patch Approvals
Unified Management | Command | 21-Q2 | Automated Patching (Policy automation)
Expert Services | ITSM | 21-Q1 | Integrate Five9 with ConnectWise for Phone & Chat Integration for HD
Platform Services | Platform Services | 21-Q3 | Ability to Add & Manage apps in IAM
Platform Services | Platform Services | 21-Q2 | IAM User Management
Unified Management | Command | 21-Q2 | Policy updates for OS Patching GA
Unified Management | Command | 21-Q1 | AccuSearch in Devices
Unified Management | Command | 21-Q2 | Permissions Set for Device Groups
Unified Management | Command | 21-Q2 | Intuitively Create and Manage Device Groups
Unified Management | Command | 21-Q2 | Critical Criteria Added to Dynamic Device Groups
Unified Management | Command | 21-Q2 | New Page to View and Analyze Device Groups
Unified Management | Command | 21-Q2 | Control Linux Agent Deployment and Launch
Unified Management | Command | 21-Q2 | Control Remote Access in Command on Mobile
Unified Management | Command | 21-Q2 | Launch Control with 1-Click stored credentials
Unified Management | Command | 21-Q2 | Control Mac Agent Deployment and Launch
Unified Management | Command | 21-Q2 | Backup portal Control integration
Unified Management | Command | 21-Q1 | End-user portal Control integration
Unified Management | Command | 21-Q1 | Push Control to LMI Endpoints
Unified Management | Command | 21-Q1 | Control Remote Access reporting in Command
Unified Management | Command | 21-Q2 | Retire LogMeIn Pro in Command
Unified Management | Command | 21-Q3 | 2021 Q3 Service and process monitors can be defined for Mac and Linux endpoints
Unified Management | Command | 21-Q3 | 2021 Q3 Custom monitors functionality for non-admin users
Unified Management | Command | 21-Q3 | 2021 Q2 Application Install/Uninstall monitor
Unified Management | Command | 21-Q3 | 2021 Q3 Network (ICMP, SNMP, Public IP, ports) monitors
Unified Management | Command | 21-Q3 | 2021 Q3 Registry and file system monitors
Unified Management | Command | 21-Q2 | 2021 Q2 Monitors support device groups (Static & Dynamic) as target endpoints
Unified Management | Command | 21-Q2 | 2021 Q3 Scripts based monitor
Unified Management | Command | 21-Q3 | 2021 Q3 Monitors can be combined into complex conditiions
Unified Management | Command | 21-Q1 | Automation configuration against Monitors Alerts (Pre-defined & Custom)
Unified Management | Command | 21-Q2 | 2021 Q3 Performance monitors
Unified Management | Command | 21-Q2 | 2021 Q2 Event monitors
Unified Management | BDR | 21-Q2 | Integrate the Acronis Cyber Protect product with the ConnectWise Platform
Platform Services | Platform Services | 21-Q2 | Enhanced Security Roles
Platform Services | Platform Services | 21-Q4 | Decouple Portal From Manage
Platform Services | Platform Services | 21-Q3 | Customer Portal Enhancements
Platform Services | Platform Services | 21-Q3 | Admin Portal Enhancements
Platform Services | Platform Services | 21-Q1 | Multiple Portals
Business Management | Business Management | 21-Q2 | BrightGauge Essentials Rollout
Business Management | Business Management | 21-Q1 | BrightGauge Essentials for Platform Reporting
Business Management | Business Management | 21-Q1 | Business Insights Pilot
Business Management | Business Management | 21-Q2 | Business Insights Phase 1
Unified Management | BDR | 21-Q2 | Recover - Backup Performance Improvement
Unified Management | Automate | 21-Q1 | AUTO-Patching Config in Web: Microsoft Reboot Policy Configuration Screen
Unified Management | Automate | 21-Q2 | AUTO-Patching Config in Web: Group and Policy Management
Unified Management | Automate | 21-Q1 | AUTO-Patching Config in Web: Third Party Update Policy Configuration Screen
Unified Management | Command | 21-Q2 | Conditions Migration from 1.0 to 2.0
Unified Management | Command | 21-Q2 | Automation against the IntelliMon Alert & Custom Monitor
Unified Management | Command | 21-Q2 | Suspension 2.0 System